## Sheet1
Stories
Titel | Task | Beschreibung | Wer | Done
Seitenstruktur | 2.1 | Specify a site map, i.e. a hierarchical list of included pages. Think about the navigation between these pages and the workflow for your potential customers. |  | obsolet
HTML Struktur | 2.2 | Generate the HTML or XHTML code for the main page of your Web site. Use <div>-elements for the main areas of the page. Fill your page with dummy information for testing. Do not use text formatting or other style information (will be done later with CSS). You may use images as decoration or to add a logo. |  | obsolet
Template | 12.2 | Using templates, try to reduce the amount of HTML code in your PHP scripts. For this, you may want to try out one of the existing HTML template systems (e.g. vLib or Smarty).
CSS Design | 2.3 | Decide how your Web shop pages should look like (colors, fonts, etc.). Specify all the necessary style information in the external CSS file. It is recommended to ▶ use class-attributes to group similar elements of your page, ▶ assign id-attributes to access the elements in the CSS file. | alle
Content | 3.2 | One of your pages should contain the list of products you offer (product number, description, price, etc.). | Kai | done
PHP - Navigation | 4.2 | Replace the HTML navigation menu in the main page of your Web site by PHP. For this, store the names of each menu item in an indexed array. Do the same for corresponding links, i.e., use another indexed array (alternatively, you may use a two-dimensional array for both). Write the necessary PHP code to transform the array contents into the "old" HTML navigation menu. | Kai | done
PHP - Products | 4.3 | Do the same for the list of products, i.e., put all the information (product name, price etc.) in one- or multi-dimensional arrays and write the PHP code to display it as HTML. | Alle | done
PHP - Products | 9.2 | Define classes for single products and for the entire product catalog. Use it to replace any existing array-based implementation. The goal is to make your implementation more flexible with respect to the upcoming data base integration. | Kai | done
PHP - External Files | 5.1 | Export the PHP code for the menu and the list of products to external files. Use the menu file to build up the navigation menu in all pages of your Web site. Modify the PHP code such that the menu item of the actual page gets a different appearance (background color, bold face, no link) or completely disappears in the navigation menu. If you decide to change the appearance, do it properly with CSS (e.g. using the class attribute). Try to export other elements of your pages into external files. The goal is to have a small set of very slim HTML files, which define only the page frames (using div-elements) while retrieving their contents from external PHP files. |  | done
PHP - Multi Page | 5.2 | Give each page of your site an ID and try to merge all your pages into a single PHP page (similar to the multi-page example discussed in class). The resulting main page may still be linked to external files (e.g. one external file per page). | Kai | done
PHP - Multilingual | 5.3 | Make your page at least bilingual, e.g. German/French. For this, move all text snippets of your pages into one or several two-dimensional arrays, where one dimension makes the distinction between the supported languages. ▶ Examples: $menuItems[0]["de"]="Seite 1" $menuItems[0]["fr"]="Page 1" $menuItems[1]["de"]="Seite 2" $menuItems[1]["fr"]="Page 2" $menuItems[2]["de"]="Seite 3" $menuItems[2]["fr"]="Page 3" $generalText[0]["de"]="Willkommen!" $generalText[0]["fr"]="Bonjour!" $generalText[1]["de"]="Produkteliste:" $generalText[1]["fr"]="Liste de produits:" | Kai | done
PHP - Multilingual | 5.3 | Let user chose the language and set his settings to a global variable | Kai | done
PHP - Multilingual | 8.1 | Implement the handling of the selected language by using a cookie (i.e., get rid of the current URL query string implementation). The browser will then "remember" the preferred language when a client revisits the shop | Kai | done
PHP - Checkout | 6.1 | Add corresponding "Buy Now" links or buttons to your products (if you have a list of products on a single page, add a button or link to each list item; if you display products individually in the main page area, add buttons or links there). | Riedo
PHP - Checkout | 6.2 | After selecting a "Buy Now" link or button, display a new page with additional product options (e.g., customization options or recommended accessories) plus further options such as "Shipping Method", "Payment Method", "Gift Box", etc. For this, use radio buttons and check boxes. | Riedo
PHP - Checkout | 6.3 | Transmit the selected options to a new page with a form for entering the client's name, e-mail, and shipping address. Use different form elements, e.g., a selection list for different countries or a textarea element for a comment. | Riedo
PHP - Checkout | 6.4 | Transmit all the entered data to a confirmation page, which informs the client about the purchased product, the options, and shipping address. Send automatic e-mails to both the client's and the shop's official addresses. | Riedo
PHP - Checkout | 8.2 | Implement a proper shopping cart using a PHP session. Add a page where the current content of the shopping cart and the total price are displayed (you may want to include this in a side bar of the main page). It must be possible to add/remove items from the cart, and there must be a "checkout" link to navigate to the (already existing) order forms. | Riedo
PHP - Checkout | 9.1 | Refactor the shopping cart using OOP. Define a class ShoppingCart with methods for adding items, removing items, emptying the cart, calculating the total price, displaying the cart as HTML, etc. For this, you may want/need to introduce additional classes, e.g., for individual shopping cart items. Store the shopping cart object in a PHP session variable to pass it from one HTTP request to another. | Riedo
Code Beautification | 6.5 | Make sure you are following the usual code conventions and have sufficient comments for others to understand your code. ▶ Simplify your code by extracting appropriate PHP functions. For example, write a function which takes a menu name and a hyperlink as input, and then produces the necessary HTML code for the navigation menu. Or you may want to define a function to generate the entire navigation menu or the list of products. Or… ▶ Try to make your code as compact and flexible as possible, e.g. by strictly separating PHP and HTML code. | Alle
JavaScript - Confirmation | 7.1 | At the end of the ordering process, display a JavaScript confirmation box to inform the user that he/she is about to enter a binding contract of purchase. Don't proceed in case the user clicks "Cancel". | Riedo
JavaScript - Form Validation | 7.2 | Install corresponding functions to validate the entered data, i.e. check that no required field remains empty, that phone numbers are real phone numbers, ZIP codes are real ZIP codes, and e-mail addresses are real e-mail addresses. Don't proceed with invalid data. ▶ (Note: For more complex validations, regular expressions will be introduced in Section 15 of the Lecture) | Riedo
Regular Expressions | 12.3 | Use regular expressions to simplify any complex string manipulations in your code. In particular, try to improve the validation of the user's input data, in which case you may need to use the JavaScript (client-side) or PHP (server-side) functionalities for regular expressions | Riedo
JavaScript - DHTML | 7.3 | Make your page a bit more interactive and dynamic using DHTML techniques. For example, highlight a menu item when hit by the mouse pointer, add a system clock, install collapsing product information or collapsing sub-menus, | Kai
PHP - Session | 8.3 | At some place on your main page, add account login forms (username, password). At the moment, do not worry about valid/invalid username/passwords pairs, just accept any combination (we will later handle that with a database). Once a user is logged in, display "Logged in as <username>" instead of the login forms. Add a link or button to log out. | Riedo
PHP - OO | 9.3 | Review your entire code for other class candidates… [to reimplement as classes] | Alle
SQL - DB | 10.1 | Work out the database schema for your Web site. The DB should at least contain tables for the products and their options. Additionally, you may include tables for orders, customers, user accounts, menus, languages, etc. Specify all the necessary table attributes, their data types, and the primary keys. Make sure your DB does not contain redundancies (1st and 2nd normal form). | Kai | done
SQL - DB | 10.2 | Use myPhpAdmin (or any other administration tool) to generate the tables according to your specification. Fill the tables with the data from your Web site. | Kai | done
SQL - DB | 10.3 | Realize the interface for reading and writing data between your newly created MySQL tables and the existing array-based or object-oriented implementation (using mysqli or propel) | Kai | done
SQL - DB | 10.4 | Write a PHP script to manage the content of your DB tables (insert, delete, update). This script can be completely independent of your Web site, but some of you may want to extend it into a fully integrated administrator area | Kai | begonnen
REST | 11.1 | Pick a REST of SOAP service of your choice and integrate it into your shop. | Kai | begonnen
Ajax | 12.1 | Add some AJAX-based effects to your Web shop to speed up the user interaction. You could for example add a product search page, which shows you the resulting product list as soon as you start typing the query. Or you could load and show a detailed product description as soon as you click on or move your mouse over a product. | Riedo